## Tabellenblatt1
| Timezone |  |  |  | Jam Link: | https://itch.io/jam/pirate |  |  | SDD = Software Design Document
IAmAMerlin | MEZ | https://www.google.com/search?q=berlin+time | [6 empty] | GDD = Game De....
Nose_knows | EST | https://www.google.com/search?q=est+time |  |  | 6 hours
Sislen | EST | https://www.google.com/search?q=est+time |  |  | Timediff!
Higan | EST | https://www.google.com/search?q=est+time
Yaseki | PST | https://www.google.com/search?q=pst+time |  |  | 9 hours!!!
| Please cross everyday that you will not be reachable/working on the gamejam! |  |  |  |  | Just enter a "X"
| 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27
IAmAMerlin
Nose_knows | bar: 2023-01-25 to 2023-01-26
Sislen
Yaseki
Higan | 2023-01-12: All day; 2023-01-20: X; 2023-01-21: All day; 2023-01-22: All day; 2023-01-23: All day
| General timetable for the development until we know more about the theme. | [9 empty] | Monday |  |  |  | 1 DAY !!!! due to TIMEZONES
| 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27
Brainstorming
Finish SDD/GDD Draft
Create Prototype
[11 empty] | Bug Fixing |  |  |  | PREP FOR HANDIN
| Start MEZ | [5 empty] | GDD DRAFT DONE! |  |  | MUSIC IS DONE! |  |  |  | 12 HOUR MEETING |  | End MEZ
| 15:00 | [7 empty] | UI CODE/ LOGIC DONE! | [6 empty] | 3:00
UI ART DONE!
[8 empty] | Teamname | LandratsSoftware
[8 empty] | Gamename | Mycelium Roads
| New meeting | on 12th of January |  | First meeting at |  |  |  | LAST MEETING |  | on 25th of January
IAmAMerlin | 2023-01-12: all day; 2023-01-15: 3PM PST; 2023-01-19: IAmAMerlin; 2023-01-20: all day
nose_knows | 2023-01-12: all day; 2023-01-19: nose_knows; 2023-01-20: XXX
Sislen | 2023-01-12: After 10:30am; 2023-01-19: Sislen; 2023-01-20: from 12:00
yaseki | 2023-01-12: 6am to 9am; 2023-01-13: 3pm to 7pm; 2023-01-19: yaseki; 2023-01-20: all day EXCEPT 1pm-3pm
[8 empty] | Higan | all day
| New meeting | on 14th of January
IAmAMerlin | 2023-01-12: all day; 2023-01-15: 21:00
nose_knows | 2023-01-12: all day; 2023-01-15: 15:00
Sislen | 2023-01-12: Pretty much all day; 2023-01-15: 15:00
yaseki | 2023-01-12: 6am-9am PST; 2023-01-13: (all day on Sunday); 2023-01-15: 12:00
| New meeting | on 17th of January
IAmAMerlin | 2023-01-12: all day; 2023-01-14: Midnight; 2023-01-15: Midnight
nose_knows | 2023-01-12: 12pm-3pm; 2023-01-13: 6pm-8pm; 2023-01-14: 6pm; 2023-01-15: 18:00
Sislen | 2023-01-12: all day; 2023-01-14: 6pm; 2023-01-15: 18:00
yaseki | 2023-01-12: all day; 2023-01-14: 3pm; 2023-01-15: 15:00
Higan | 2023-01-12: all day; 2023-01-13: all day; 2023-01-14: 6pm; 2023-01-15: 18:00